Japanese Maple Atlas

RC-020 Visual Atlas Roadmap

Integrated Three-Track Operating Plan

Version 1.1 — Approved and governing

Effective planning date: 26 July 2026

Document purpose Unify engineering, editorial/content production, and media/visual-asset work into one coordinated operating plan, while preserving independent execution in separate conversations and a single repository validation and publication gate.

Repository: github.com/JorisMB82/japanese-maple-atlas

Production: japanese-maple-atlas.vercel.app

Prepared from the attached Post-Sprint-10 roadmap and the current repository baseline.

# Document control and revision scope

| Field | Value |
| --- | --- |
| Document ID | ROADMAP-002 / Integrated Operating Plan |
| Version | 1.1 — Approved and governing |
| Governing milestone | Japanese Maple Atlas — RC-020 Visual Reference Release |
| Secondary milestone | RC-025 corpus and Version 1.0 readiness decision |
| Repository source of truth | main |
| Current baseline date | 26 July 2026 |
| Approval record | Approved by the project owner on 26 July 2026. This version is the governing operating-plan baseline, subject to repository commit and normal change control. |
| Approval authority | Project owner — Joris Magenti |
| Approval date | 26 July 2026 |
| Decision Record | DR-ROADMAP-002-001 — Approval of ROADMAP-002 Version 1.1 Integrated Three-Track Operating Plan |

## What changes in version 1.1

Updates the programme baseline to recognise that Sprint 11 scalable ingestion is present on current main.

Expands the earlier three-track concept into an executable operating model with ownership, handoffs, stage gates, work-in-progress controls and publication sequencing.

Extends coordinated corpus planning from RC-020 through RC-025 without weakening the RC-020 release gate.

Clarifies that the RC-006 compiler integration proof is not automatically a completed botanical Reference Standard.

Adds branch and file-ownership rules so separate engineering, editorial and media conversations can work in parallel without overwriting one another.

Adds copy-ready launch prompts for the editorial/content-production stream and the media/visual-assets stream.

Change-control note ROADMAP-002 Version 1.1 was approved by the project owner on 26 July 2026 and is governed by DR-ROADMAP-002-001. Future material changes require a new or superseding Decision Record.

# Contents

1. Authoritative context and current baseline

2. Strategic objective and milestone structure

3. Revised roadmap after Sprint 10

4. Integrated three-track operating model

5. Record-level production lifecycle and stage gates

6. Ownership, handoffs and cross-chat coordination

7. Wave plan for RC-006 through RC-025

8. Publication gates and quality controls

9. Operating cadence, status reporting and change control

10. Immediate directive

Appendix A — Editorial/content-production stream launch prompt

Appendix B — Media/visual-assets stream launch prompt

Appendix C — Authoritative links and repository paths

# 1. Authoritative context and current baseline

The Japanese Maple Atlas is a repository-first, evidence-aware botanical knowledge platform. The repository is authoritative; the public application is a derived interface. Only approved, validated repository knowledge may reach production.

## 1.1 Current repository baseline

| Baseline item | Current position |
| --- | --- |
| Production source of truth | main |
| Application / repository contract | 0.11.0 baseline reflected in current README |
| Atlas Compiler | 2.0.0 |
| Public cultivar corpus | RC-001 through RC-005 |
| First-class repository objects | 235 |
| Sprint 11 status | Scalable ingestion implementation present; canonical RC-006+ contract, legacy adapters, preflight/dry-run, transactional publication and 20/25/150-record scale validation delivered. |
| Sprint 11.5 status | Media-governance implementation and systematic visual-asset pipeline remain the next foundation work. |
| RC-006 status | Compiler integration proof exists, but a completed public botanical RC-006 is not established by that proof alone. |

## 1.2 Authoritative project principles

The repository is the source of truth; generated JSON and registries are never edited manually.

Major botanical, editorial, architectural and governance decisions remain traceable through Decision Records.

Reference Standards must distinguish evidence, interpretation, uncertainty, rejected claims and future-review conditions.

Visual attractiveness does not establish cultivar identity; editorial and evidentiary media status remain separate.

Public AI, broad SDKs, runtime APIs and unrelated platform expansion remain deferred until the RC-020 milestone is secure.

Quality is protected through fixed acceptance gates rather than by indefinite, unbounded sprints.

# 2. Strategic objective and milestone structure

Locked near-term objective Transform the Atlas from a technically successful five-cultivar pilot into a credible twenty-cultivar visual and evidence-aware reference product, then extend the validated publication system through RC-025 for the Version 1.0 readiness decision.

## 2.1 RC-020 Visual Reference Release

Twenty completed and approved Reference Standards: RC-001 through RC-020.

Governed, high-quality visual representation for every cultivar.

Accurate botanical drawings or identity plates where suitable photographs are unavailable.

Generic, scalable and transactional compiler ingestion.

Strong evidence, rights, provenance and accessibility controls.

A production interface useful for identification, comparison, learning and reference.

Real-user validation, performance hardening and a formal release audit.

## 2.2 RC-025 and Version 1.0 readiness

Complete RC-021 through RC-025 after incorporating RC-020 product findings.

Stabilise the publication contract, versioned static data and machine-readable discovery.

Decide whether Version 1.0 is justified by corpus quality, product stability and publication maturity—not by record count alone.

## 2.3 Deferred scope

Public repository-aware AI assistant

Full runtime API and SDK suite

Community editing

Broad platform abstraction

Expansion into orchids or other botanical domains

# 3. Revised roadmap after Sprint 10

## Phase 1 — Platform foundation

Status: Complete through Sprint 10, with Sprint 11 scalable ingestion now present on current main.

Repository-first architecture

Compiler and validation system

Structured object model

Search, graph and relationships

Atlas Explorer

Testing and quality infrastructure

Production deployment and rollback architecture

## Phase 2 — RC-020 Visual Atlas milestone

| Work package | Purpose | Operating position | Exit criterion |
| --- | --- | --- | --- |
| Sprint 11 | Compiler and repository scale generalisation | Implemented on current baseline; verify merge/review state before downstream integration. | RC-006 can be ingested without cultivar-specific compiler code. |
| Sprint 11.5 | Media governance and visual-asset pipeline | Next engineering/media foundation; may run in parallel with editorial research. | Every cultivar can receive rights-compliant, traceable visual assets through a repeatable process. |
| Sprint 12 | Editorial production system; RC-006–RC-010 | First live content wave. | Five new RCs published with governed visuals and consistent quality. |
| Sprint 12.1 | RC-011–RC-015 content wave | Repeatability and production-speed improvement. | Fifteen cultivars production-ready. |
| Sprint 12.2 | RC-016–RC-020 content wave | Complete immediate corpus milestone. | RC-001–RC-020 approved, compiled, visually represented and deployed. |
| Sprint 13 | RC-020 product validation | Representative user testing and value-proposition validation. | Critical usability findings resolved or documented. |
| Sprint 14 | Performance, accessibility and operational hardening | Run against the real media-rich twenty-record corpus. | Defined operational thresholds met. |
| Sprint 15 | RC-020 release audit | Formal release gate. | RC-020 Visual Reference Release approved. |

## Phase 3 — RC-025 and Version 1.0 decision

Produce RC-021–RC-025 through the same governed pipeline.

Apply RC-020 user and operational findings.

Stabilise the publication contract and machine-readable release surface.

Perform a Version 1.0 readiness audit.

## Phase 4 — RC-026–RC-150

Treat later records as a continuous editorial publication programme supported by periodic engineering-maintenance releases. Suggested waves remain RC-026–040, RC-041–060, RC-061–080, RC-081–100, RC-101–125 and RC-126–150.

# 4. Integrated three-track operating model

Operating model Engineering, editorial/content and media/visual-assets work proceed in separate conversations and may develop concurrently. They remain one programme because they share identifiers, contracts, Decision Records, repository paths, validation commands and a common publication gate.

| Track | Primary scope | Primary file ownership | Required handoff |
| --- | --- | --- | --- |
| 1. Engineering and platform | Generic compiler, contracts, schemas, validation, media pipeline, derivatives, interface, performance, CI, deployment. | Engineering files; contract and schema changes; generated-output systems. | Approved contract, passing validation/build, migration notes, exact changed-file list and integration readiness. |
| 2. Editorial and content production | Cultivar selection, evidence discovery, source evaluation, assertion extraction, drafting, conflict review, botanical review, naming, uncertainty, relationships and freeze decisions. | RC Markdown and source sidecars; editorial Decision Records; evidence registers. | Approved/frozen RC, approved source sidecar, relationship proposals, review record and handoff package. |
| 3. Media and visual assets | Photo audit/acquisition, rights clearance, provenance, specimen identity, illustration, derivatives, captions, alt text and coverage tracking. | Media sidecars, source assets, derivative specifications, rights evidence and accessibility text. | Approved primary visual or governed gap treatment; complete rights/provenance metadata; integration-ready media package. |

## 4.1 Non-overlap rules

Engineering does not rewrite approved botanical prose merely to simplify parsing; compatibility belongs in governed contracts or adapters.

Editorial does not modify compiler, schema, generated repository outputs or media pipeline code.

Media does not silently alter cultivar identity claims or treat a visually plausible image as identity evidence.

No track edits generated JSON under atlas-repository outputs or lib/repository-registry.js directly.

When two tracks need the same file, ownership is assigned before editing and the other track provides a structured change request rather than a competing version.

## 4.2 Shared programme artefacts

| Artefact | Purpose | Owner |
| --- | --- | --- |
| Roadmap and Decision Records | Programme scope, milestone rules, exceptions and decisions. | Project owner / programme governance |
| RC-###.md | Frozen cultivar Reference Standard. | Editorial |
| RC-###.sources.json | Underlying sources and evidence-domain mappings. | Editorial |
| RC-###.media.json | Governed media assets and metadata. | Media |
| Contract and schema files | Canonical profile, vocabularies, compatibility and validation. | Engineering, with editorial/media consultation |
| Coverage and status register | Cross-track stage, blocker and next-gate visibility for each RC. | Programme owner; each track updates its fields |
| Validation and release evidence | Preflight, compile, tests, build, regression and deployment proof. | Engineering/integration |

## 4.3 Definition of a complete cultivar package

Approved and frozen RC Markdown file using the canonical profile or an approved governed exception.

Approved underlying-source sidecar with evidence-domain coverage and source locators.

Naming, synonyms, uncertainty and relationship treatment reviewed across the corpus.

At least one approved primary visual, or a documented governed visual gap with an approved drawing plan.

Complete media sidecar with rights, creator, provenance, evidentiary status, caption and alt text.

Compiler preflight, dry-run and repository validation pass.

Production profile, search, comparison and relevant graph relationships verified.

Publication decision, changed-file list, hashes and release evidence recorded.

# 5. Record-level production lifecycle and stage gates

| Gate | Meaning | Minimum evidence to advance |
| --- | --- | --- |
| G0 — Planned | Cultivar is selected, assigned a stable RC identifier and placed in a wave. | Approved selection rationale; no duplicate or conflicting RC assignment. |
| G1 — Research ready | Research brief, target questions and source strategy exist. | Minimum source classes identified; likely identity/naming risks recorded. |
| G2 — Evidence assembled | Sources are assessed and material assertions extracted. | Evidence matrix, source locators, conflicts, uncertainties, unresolved and rejected claims documented. |
| G3 — Editorial draft complete | Canonical RC draft and source sidecar are complete. | All required sections/metadata present; controlled vocabularies applied; self-review complete. |
| G4 — Botanical/editorial approval | Identity, nomenclature, morphology, horticulture and uncertainty pass review. | Required corrections closed; freeze candidate approved subject to media and integration. |
| G5 — Media ready | Primary visual and supporting media package are approved or a governed gap is accepted. | Rights/provenance, evidentiary status, caption, alt text and derivative plan complete. |
| G6 — Integration ready | RC, source and media sidecars form one coherent package. | Identifiers match; relationships and cross-record references resolve; no ownership conflict remains. |
| G7 — Technical validation | Preflight, dry-run, compile, repository checks, tests and production build pass. | No malformed record, object drift, broken route, rights check or missing required media. |
| G8 — Frozen and published | Editor-in-Chief approves freeze and production publication. | Approved/frozen status, version/date, Decision Record and deployment evidence recorded. |
| G9 — Post-publication review | Production page is inspected and feedback is triaged. | Critical defect absent; non-critical findings logged for next wave or maintenance release. |

## 5.1 Work-in-progress limits

No more than five RCs should be active in one publication wave.

Within a wave, no more than two RCs should normally be in deep drafting before the first record reaches botanical review; this exposes template problems early.

Media acquisition may cover the full wave, but rights-uncertain assets must not be treated as committed publication assets.

Unresolved identity or nomenclature questions block freeze but do not necessarily block research on the next RC.

A blocked record remains visible in the wave register with a named decision owner and next action.

# 6. Ownership, handoffs and cross-chat coordination

## 6.1 Responsibility matrix

| Activity | Engineering | Editorial | Media | Project owner / Editor-in-Chief |
| --- | --- | --- | --- | --- |
| Roadmap, milestone and scope changes | A | C | C | R |
| Canonical RC contract / compiler profile | R/A | C | C | I |
| Cultivar selection and RC numbering | C | R | C | A |
| Source discovery and evidence synthesis | I | R/A | C | A at freeze |
| RC drafting and cross-record consistency | I | R/A | C | A at freeze |
| Media governance and rights classification | C | C | R/A | A for public use |
| Photograph/drawing selection | I | C | R | A |
| Compiler preflight and repository validation | R/A | C | C | I |
| Production deployment | R | I | I | A |
| Release audit | R | R | R | A |

R = Responsible; A = Accountable; C = Consulted; I = Informed. The project owner may delegate review work but retains final freeze and public-release authority.

## 6.2 Mandatory handoff packet

Baseline: repository, branch and commit SHA inspected.

Scope: RC numbers and exact files owned by the track.

Completed work: concise summary tied to gates.

Changed files: exact repository-relative list.

Validation: commands run and results, including failures or skipped checks.

Open issues: evidence conflicts, rights gaps, schema needs or decisions required.

Next receiver: which track must act and the precise requested action.

Readiness statement: explicit PASS, CONDITIONAL or BLOCKED for the next gate.

## 6.3 Cross-chat coordination protocol

Every conversation begins by inspecting current main; it must not rely solely on an earlier handoff summary.

Each conversation records the exact baseline commit SHA before creating or evaluating changes.

No conversation assumes another conversation’s unmerged local files exist. Only merged repository content or explicitly uploaded handoff files are authoritative.

Parallel branches should avoid editing the same file. Recommended branch families are engineering/, content/ and media/.

Contract or schema changes merge before dependent RC or media packages are integrated.

Before publication, the integration conversation refreshes current main and reruns the complete release-readiness sequence.

Conflicting edits are resolved by file ownership and Decision Records, not by choosing whichever chat produced the latest text.

| Track | Recommended branch pattern | Notes |
| --- | --- | --- |
| Engineering | engineering/sprint-11-5-media-pipeline or engineering/<maintenance-scope> | Contracts, schemas, scripts, application and CI. |
| Editorial | content/rc-006-010, content/rc-011-015, etc. | RC Markdown, source sidecars and editorial decisions. |
| Media | media/rc-001-010, media/rc-011-020, etc. | Media sidecars, governed assets and derivative metadata. |
| Integration | integration/rc-###-wave or controlled merge sequence | Final combined validation and release evidence. |

# 7. Wave plan for RC-006 through RC-025

## 7.1 Immediate sequencing

Confirm current main and close Sprint 11 review/merge questions, if any.

Run Sprint 11.5 media-governance foundation and RC-001–RC-005 visual audit.

In parallel, verify RC-006 status and lock cultivar assignments for RC-006–RC-020.

Begin the first editorial wave; use RC-006 unless it is demonstrably assigned and in progress elsewhere, in which case register that dependency and begin RC-007.

Integrate and publish in five-record waves, with a formative checkpoint at RC-010.

Complete RC-020 user validation, hardening and release audit.

Produce RC-021–RC-025 using the corrected system and perform the Version 1.0 readiness decision.

## 7.2 Cohort plan

| Cohort | RC range | Primary objective | Roadmap package |
| --- | --- | --- | --- |
| Foundation uplift | RC-001–RC-005 | Media audit and uplift; preserve frozen RC text unless a governed correction process is invoked. | Sprint 11.5 |
| Wave 1 | RC-006–RC-010 | Prove live editorial production and canonical ingestion; run RC-010 formative checkpoint. | Sprint 12 |
| Wave 2 | RC-011–RC-015 | Improve repeatability, source reuse, review checklists and media acquisition. | Sprint 12.1 |
| Wave 3 | RC-016–RC-020 | Complete the public milestone and stress-test product quality. | Sprint 12.2 |
| Validation / release | RC-001–RC-020 | User testing, hardening and release audit. | Sprints 13–15 |
| Wave 4 | RC-021–RC-025 | Apply findings and reach the Version 1.0 decision threshold. | Phase 3 |

## 7.3 Master RC operating register

| Record | Cohort | Editorial status | Media status | Publication |
| --- | --- | --- | --- | --- |
| RC-001 | Foundation | Frozen | Audit/uplift | Published baseline |
| RC-002 | Foundation | Frozen | Audit/uplift | Published baseline |
| RC-003 | Foundation | Frozen | Audit/uplift | Published baseline |
| RC-004 | Foundation | Frozen | Audit/uplift | Published baseline |
| RC-005 | Foundation | Frozen | Audit/uplift | Published baseline |
| RC-006 | Wave 1 | Status confirm / first production RC | Plan | Not public |
| RC-007 | Wave 1 | Planned | Plan | Not public |
| RC-008 | Wave 1 | Planned | Plan | Not public |
| RC-009 | Wave 1 | Planned | Plan | Not public |
| RC-010 | Wave 1 | Planned | Plan | Not public |
| RC-011 | Wave 2 | Planned | Plan | Not public |
| RC-012 | Wave 2 | Planned | Plan | Not public |
| RC-013 | Wave 2 | Planned | Plan | Not public |
| RC-014 | Wave 2 | Planned | Plan | Not public |
| RC-015 | Wave 2 | Planned | Plan | Not public |
| RC-016 | Wave 3 | Planned | Plan | Not public |
| RC-017 | Wave 3 | Planned | Plan | Not public |
| RC-018 | Wave 3 | Planned | Plan | Not public |
| RC-019 | Wave 3 | Planned | Plan | Not public |
| RC-020 | Wave 3 | Planned | Plan | Not public |
| RC-021 | Wave 4 | Post-RC-020 | Post-RC-020 | Not public |
| RC-022 | Wave 4 | Post-RC-020 | Post-RC-020 | Not public |
| RC-023 | Wave 4 | Post-RC-020 | Post-RC-020 | Not public |
| RC-024 | Wave 4 | Post-RC-020 | Post-RC-020 | Not public |
| RC-025 | Wave 4 | Post-RC-020 | Post-RC-020 | Not public |

The operating register is a starting state, not a claim that cultivar assignments are locked. Add cultivar names, blockers, next gate, responsible reviewer and target freeze date once selection is approved.

# 8. Publication gates and quality controls

## 8.1 Per-record publication gate

RC file is approved and frozen; required metadata and sections are complete.

Source sidecar is approved; required evidence domains are covered and locators are present.

Contradictory evidence, uncertainty and rejected claims are documented.

Naming, synonym and relationship rules are applied consistently.

Primary visual is approved or governed gap treatment is accepted.

Rights, creator attribution, provenance, evidentiary status, caption and alt text are complete.

All identifiers agree across RC, source and media files.

Preflight and dry-run pass without record-level errors.

Full repository validation, tests, build and regression checks pass.

Production page and search/comparison behaviour are inspected after deployment.

## 8.2 Wave publication gate

All records in the wave meet the per-record gate or are explicitly excluded from the release.

Cross-record terminology, measurements, synonym policy, confidence language and relationship density are reviewed.

Object counts, search coverage, graph inventory and manifests are dynamic and internally consistent.

No unlicensed, unattributed or misleading visual asset is included.

Changed-file list, hashes, validation evidence, commit message and merge instructions are complete.

Rollback remains possible and the previous approved production state is preserved until deployment succeeds.

## 8.3 RC-020 release audit

| Domain | Acceptance condition |
| --- | --- |
| Content | RC-001–RC-020 approved; no required sections unresolved; evidence minimums met; contradictions and naming rules documented. |
| Media | Approved primary visual per cultivar or approved gap; rights and attribution complete; derivatives, captions and alt text reviewed. |
| Engineering | Generic compiler, no permanent five-record assumptions, 150-record scale test, validation/build/deployment/rollback pass. |
| Product | Useful search and comparison, real-user testing complete, critical findings resolved, public pages and structured outputs stable. |

# 9. Operating cadence, status reporting and change control

## 9.1 Coordination cadence

| Trigger | Required action |
| --- | --- |
| At conversation start | Inspect current main, record baseline SHA, review relevant handoff and declare owned files. |
| At each gate | Update the RC operating register and produce the mandatory handoff packet. |
| At each five-record wave | Run cross-record editorial review, media coverage review and full integration validation. |
| At RC-010 | Run the formative checkpoint before scaling the next ten records. |
| At RC-020 | Run user validation, hardening and formal release audit. |
| At material scope change | Create or update a Decision Record before implementation. |

## 9.2 Status language

| Status | Definition |
| --- | --- |
| PLANNED | Assigned to a wave but work has not begun. |
| ACTIVE | Work is in progress and the owned files are identified. |
| REVIEW | A defined reviewer or track is evaluating the package. |
| BLOCKED | A named decision, source, right, technical fix or user input prevents advancement. |
| READY | All criteria for the next gate are met. |
| FROZEN | Editorially approved; changes require governed correction/versioning. |
| PUBLISHED | Validated and deployed in production. |
| SUPERSEDED | Replaced by a newer approved version with traceable history. |

## 9.3 Decision-record triggers

Changing the RC-020 milestone definition or Version 1.0 threshold.

Changing canonical RC sections, metadata, controlled vocabularies or evidence minimums.

Approving a compiler exception or legacy treatment.

Accepting unresolved cultivar identity, synonym or provenance ambiguity at freeze.

Using synthetic or reconstructed media in a new evidentiary role.

Changing licence, rights, privacy or retention policy.

Publishing a record that does not satisfy a standard gate.

Reversing a previously approved methodological or editorial decision.

# 10. Immediate directive

Current programme directive Operate the three tracks in parallel from current main. Engineering focuses on Sprint 11.5 and integration support; editorial verifies RC-006 status and begins the first content wave; media audits RC-001–RC-005 and establishes the governed asset pipeline. All work converges at the record-level and wave-level publication gates.

## 10.1 Next actions by track

| Owner | Immediate action |
| --- | --- |
| Engineering | Confirm Sprint 11 baseline; implement or finalise Sprint 11.5 media governance, asset validation, derivatives and coverage checks; publish exact contract requirements to the other tracks. |
| Editorial | Inspect RC-001–RC-005 and the canonical template; confirm RC-006 status; lock cultivar assignments; begin the first record and source sidecar through G3/G4. |
| Media | Audit current identity plates and sidecars; define rights/provenance and derivative requirements; build RC-001–RC-020 coverage matrix; begin primary-visual acquisition for Wave 1. |
| Programme owner | Commit the approved v1.1 roadmap and Decision Record, resolve RC-006 ownership, approve the cultivar list and reviewers, and enforce the common publication gate. |

# Appendix A — Editorial/content-production stream launch prompt

Copy the prompt below into a new conversation dedicated to the editorial and content-production stream. It is deliberately bounded to establish the stream and advance the first production record without mixing engineering or media ownership.

Japanese Maple Atlas — Editorial and Content-Production Stream

You are taking over the editorial and content-production workstream for the Japanese Maple Atlas.

Authoritative project context

Repository: https://github.com/JorisMB82/japanese-maple-atlas

Production site: https://japanese-maple-atlas.vercel.app

Production source of truth: main

Current repository baseline to verify before working:

- current main reflects the post-Sprint-10 platform and Sprint 11 scalable ingestion work;

- Atlas Compiler 2.0.0 and the canonical RC-006+ contract are present;

- RC-001 through RC-005 are the frozen public Reference Standards;

- the repository still has five public cultivars; a compiler integration proof for RC-006 is not automatically a completed botanical RC-006;

- Sprint 11.5 media governance is a separate parallel workstream.

Read these sources first

1. Repository README: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/README.md

2. Governing roadmap: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/docs/ROADMAP-002_Post-Sprint-10_RC-020-Visual-Atlas-Roadmap_v1.0.md

3. Scalable ingestion contract: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/docs/COMPILER-002_Scalable-Reference-Standard-Ingestion_v1.0.md

4. Canonical RC template: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/contract/RC-TEMPLATE.md

5. Frozen reference examples:

- RC-001: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-001.md

- RC-002: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-002.md

- RC-003: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-003.md

- RC-004: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-004.md

- RC-005: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-005.md

6. Source-sidecar pattern: https://github.com/JorisMB82/japanese-maple-atlas/tree/main/atlas-repository/reference-standards/sources

Primary objective

Establish and execute the governed editorial production system for RC-006 through RC-025, while protecting the immediate RC-020 Visual Reference Release milestone. Work in controlled five-record waves: RC-006–RC-010, RC-011–RC-015, RC-016–RC-020, then RC-021–RC-025 after the RC-020 review.

First, inspect current main and determine the real status of RC-006. If no completed editorial RC-006 exists, begin with RC-006. If RC-006 is demonstrably being produced in another workstream, record that dependency and begin RC-007 without duplicating work.

Editorial responsibilities

- cultivar selection and stable RC assignment;

- source discovery and source-quality assessment;

- assertion extraction and evidence-domain mapping;

- naming, synonyms, identity and historical provenance;

- whole-plant architecture, leaf morphology and seasonal characteristics;

- horticultural guidance, propagation and cultivar continuity;

- diagnostic limits, uncertainty, conflicts, unresolved propositions and rejected claims;

- cross-record terminology and consistency;

- source sidecars and editorial Decision Records;

- botanical/editorial review and freeze recommendation.

Boundaries

- Do not modify compiler, application, schema, CI or generated repository outputs.

- Do not create or approve media rights, derivatives or media-pipeline code; provide visual requirements and hand them to the media stream.

- Do not invent sources, page references, cultivar histories or certainty.

- Use authoritative primary or institutional sources wherever possible and preserve exact source locators.

- Distinguish descriptive confidence from cultivar authentication.

- Do not rewrite RC-001 through RC-005 merely to match the new template.

- Never mark a record approved or frozen without an explicit editorial approval decision.

Required production sequence per cultivar

cultivar selection → research brief → source discovery → source assessment → evidence extraction → assertion/conflict matrix → structured draft → uncertainty review → cross-record review → media requirements handoff → botanical/editorial approval → compiler preflight handoff → freeze recommendation

Minimum deliverables for the first execution cycle

1. Report the exact current main commit SHA and the files inspected.

2. Audit the canonical template against RC-001 through RC-005 and identify reusable editorial conventions versus legacy-only structures.

3. Confirm RC-006 status and identify any conflict with another conversation.

4. Propose a balanced cultivar assignment list for RC-006 through RC-020, with a provisional RC-021 through RC-025 reserve list. Explain selection criteria such as horticultural importance, morphology, colour, habit, synonym complexity, evidence availability and visual coverage.

5. Create a concise editorial operating register showing each RC, cultivar, wave, current gate, blocker, next action and status.

6. Begin the first unassigned production record and produce:

- research brief;

- source inventory and authority assessment;

- evidence/assertion matrix with source locators;

- conflicts, uncertainties, rejected claims and open questions;

- canonical RC draft;

- draft RC-###.sources.json;

- visual requirements handoff for the media stream;

- editorial readiness assessment.

Quality and working method

- Search current web and institutional sources as necessary; cite every material factual claim.

- Prefer botanical institutions, arboreta, recognised cultivar references, registration authorities, major specialist texts and traceable nursery-origin documentation over generic commercial pages.

- Record competing interpretations and what future evidence could change the conclusion.

- Keep a clear distinction between evidence, editorial synthesis and inference.

- Work one cultivar at a time through a reviewable package; do not create twenty shallow records at once.

Return with

- baseline and repository audit;

- proposed RC-006–RC-025 assignment register;

- first-record research and draft package;

- exact files created or proposed;

- unresolved decisions and dependencies;

- a PASS / CONDITIONAL / BLOCKED assessment for botanical review and engineering preflight.

Do not claim that work is complete unless the actual files or complete draft contents are provided. Ask only if a genuinely blocking input cannot be resolved from the repository, authoritative research or the integrated roadmap.

# Appendix B — Media/visual-assets stream launch prompt

Copy the prompt below into a separate conversation dedicated to media governance, image acquisition, illustration and visual coverage.

Japanese Maple Atlas — Media and Visual-Assets Stream

You are taking over the media and visual-assets workstream for the Japanese Maple Atlas.

Authoritative project context

Repository: https://github.com/JorisMB82/japanese-maple-atlas

Production site: https://japanese-maple-atlas.vercel.app

Production source of truth: main

The immediate programme goal is the RC-020 Visual Reference Release: RC-001 through RC-020 must have governed, attractive, traceable and legally usable visual representation. RC-021 through RC-025 should be planned as the next wave, but must not distract from securing RC-020.

Read these sources first

1. Repository README: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/README.md

2. Governing roadmap: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/docs/ROADMAP-002_Post-Sprint-10_RC-020-Visual-Atlas-Roadmap_v1.0.md

3. Scalable ingestion contract: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/docs/COMPILER-002_Scalable-Reference-Standard-Ingestion_v1.0.md

4. Canonical RC template: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/contract/RC-TEMPLATE.md

5. Existing media sidecars: https://github.com/JorisMB82/japanese-maple-atlas/tree/main/atlas-repository/reference-standards/media

6. RC-001 media example: https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/media/RC-001.media.json

7. Frozen RC references:

- https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-001.md

- https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-002.md

- https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-003.md

- https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-004.md

- https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-005.md

Primary objective

Establish Sprint 11.5 as a complete, repeatable media-governance and visual-asset operating system, audit and uplift RC-001 through RC-005, and prepare governed visual coverage for RC-006 through RC-020 in coordination with the editorial stream.

Core rules

- A visually attractive image is not automatically evidence of cultivar identity.

- Every asset must have an explicit editorial role and evidentiary status.

- No image may be copied, downloaded, generated, transformed or published without documented rights and provenance appropriate to that use.

- Synthetic, reconstructed or procedural illustrations must be conspicuously labelled and must not silently represent an observed specimen.

- A drawing must not communicate greater botanical certainty than its sources justify.

- Specimen identity and cultivar confidence must be recorded separately from image quality.

- Preserve creator attribution, source lineage, original checksum and derivative relationships.

Supported visual roles

- primary cultivar profile visual;

- whole-plant habit;

- leaf or diagnostic detail;

- spring, summer and autumn foliage;

- bark, flower, samara, juvenile and mature views;

- comparison image;

- botanical observation drawing;

- evidence-based reconstruction;

- editorial illustration;

- diagrammatic identity plate.

Required media metadata

media identifier; cultivar identifier; media type; role; subject; season; photographer or illustrator; contributor; rights holder; licence and licence URI; source; capture or creation date; location granularity; specimen identity; identification confidence; editorial status; evidentiary status; original checksum; MIME type; dimensions; original-to-derivative relationship; caption; alt text; focal point; approval history; EXIF/GPS handling; retention status.

Boundaries

- Do not rewrite cultivar Reference Standards or source evidence.

- Do not modify compiler/application code unless the engineering conversation explicitly requests a specification or patch handoff.

- Do not treat licence ambiguity as permission.

- Do not use generic web search images as production assets without verified rights and source records.

- Do not generate final botanical illustrations before the editorial stream provides approved visual requirements and evidence constraints.

Minimum deliverables for the first execution cycle

1. Report the exact current main commit SHA and all media-related files and production pages inspected.

2. Audit RC-001 through RC-005:

- current asset and sidecar;

- visual role and evidentiary status;

- rights and attribution completeness;

- botanical adequacy;

- accessibility quality;

- missing whole-plant, foliage or seasonal views;

- uplift recommendation.

3. Produce a media coverage matrix for RC-001 through RC-020, with provisional planning fields for RC-021 through RC-025.

4. Define the governed media taxonomy, required metadata, statuses and approval workflow.

5. Define file naming, storage, checksums, original preservation, EXIF/GPS policy, derivative sizes, responsive-image rules, focal points and alt-text/caption review.

6. Define rights-clearance categories for original, contributed, licensed, Creative Commons, public-domain, archival, commissioned and synthetic assets.

7. Identify immediate acquisition channels and likely source institutions for Wave 1, but separate candidates from rights-cleared approved assets.

8. Produce the exact engineering handoff required to implement or validate Sprint 11.5.

9. Produce the exact editorial handoff template for requesting a photograph, drawing or identity plate for each cultivar.

Coverage tiers

- Release minimum: one approved, rights-cleared primary visual per cultivar.

- Target: whole-plant/habit plus foliage or diagnostic detail.

- Enhanced: seasonal, bark, flower, samara, juvenile, mature or comparison views where evidence permits.

- Gap treatment: approved governed drawing or explicitly documented media gap.

Return with

- current-state media audit;

- media-governance specification;

- RC-001–RC-025 coverage matrix;

- rights and provenance workflow;

- derivative and accessibility specification;

- Wave 1 acquisition/illustration plan;

- exact repository files to create or modify;

- engineering and editorial handoffs;

- unresolved rights, identity or sourcing risks;

- a PASS / CONDITIONAL / BLOCKED assessment for Sprint 11.5 implementation.

Do not claim an asset is usable until rights, provenance, specimen identity, evidentiary classification and accessibility metadata are documented. Ask only if a genuinely blocking input—such as ownership of a user-supplied photograph—cannot be resolved from the repository or source documentation.

# Appendix C — Authoritative links and repository paths

| Resource | Link |
| --- | --- |
| Repository | https://github.com/JorisMB82/japanese-maple-atlas |
| Production site | https://japanese-maple-atlas.vercel.app |
| README | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/README.md |
| ROADMAP-002 v1.0 | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/docs/ROADMAP-002_Post-Sprint-10_RC-020-Visual-Atlas-Roadmap_v1.0.md |
| Sprint 11 summary | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/SPRINT-11.md |
| Scalable ingestion contract | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/docs/COMPILER-002_Scalable-Reference-Standard-Ingestion_v1.0.md |
| Canonical RC template | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/contract/RC-TEMPLATE.md |
| RC-001 | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-001.md |
| RC-002 | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-002.md |
| RC-003 | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-003.md |
| RC-004 | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-004.md |
| RC-005 | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/RC-005.md |
| Source sidecars | https://github.com/JorisMB82/japanese-maple-atlas/tree/main/atlas-repository/reference-standards/sources |
| Media sidecars | https://github.com/JorisMB82/japanese-maple-atlas/tree/main/atlas-repository/reference-standards/media |
| RC-001 media example | https://github.com/JorisMB82/japanese-maple-atlas/blob/main/atlas-repository/reference-standards/media/RC-001.media.json |

End of ROADMAP-002 v1.1 — Integrated Three-Track Operating Plan